## Hoja1
Hours and Tasks Report for GPS50 Synchronizer Development
Services: Full-Stack Development of dynamic conecctions with Gestproject and Sage50 updtates, along with application design and code debbuging for the Customer Synchronization section Sincronización de Clientes	Week 1 (2024/08/1 – 2024/08/7)	Completion of the first functional model with static data (Reviewed in a meeting with David, José Luis, and Juan Francisco).			40
	Hours per week				40
	Week 2 (2024/08/7 – 2024/08/14)	Code base debugging and separation of concerns in projects.			5
		Integration of Gestproject procedures for dynamic loading of global styles.			5
		Integration of Gestproject procedures for dynamic data search to connect to the database.			8
		Refactoring of the "Sage50ConnectionManager" project to integrate dynamic data loading procedures from Gestproject.			10
		Design and coding of procedures for dynamic user data recall functions on different devices.			10
		Handling the persistence problem of "eurowinsys" data in Sage50 business classes.			2
	Hours per week				40
	Week 3 (2024/08/14 – 2024/08/21)	Integration of changes required in the meeting of 2024-08-14.			8
		Linking customers with company groups.			10
		Adjustments in the comparison of clients never synchronized but coincident between both programs.			6
		Removal of validations of Sage50 business classes to allow synchronization between customers.			2
		Adjustments of comparison messages between customers.			2
		Correcting the synchronization status errors.			4
		Simplifying the user interface to maintain essential and synthetic options of the process.			4
		Development of notifications and user queries for possible synchronization flows and linking of customers.			4
	Hours per week				40
	Week 4 (2024/08/21 – 2024/08/28)	Addition of the option to link existing clients without overwriting data.			8
		Debugging, testing, and product development version closure.			8
	Hours per week				16
	Section total				136

Providers Synchronization	Week 4 (2024/08/21 – 2024/08/28)		application design according to dependency injection and solid patterns		6